## Instructions
FF&E schedule template | OpenLintel • Editable XLSX resource
How to use | Agree the classification boundary with your team. In this library, furniture and the loose rug sit in this register; the retained floor belongs in the finish schedule and built-in joinery stays linked to its drawing and specification. This is a documentation convention, not a universal accounting rule. Reconcile each stable reference against the plan once, then check its specification and purchasing unit before sharing.
Example status | Illustrative teaching extension of The Window Room; not a client record, supplier quote, site survey, or construction-ready document. Pending professional review.
Getting started | Duplicate Blank Template for your project. Replace teaching examples with verified project information. Keep units and sources explicit. Nothing is uploaded to OpenLintel.
Units / currency | State units explicitly. Sample dimensions are metric and nominal, not surveyed.
Review | These are educational planning aids, not legal agreements, professional certification, or instructions for construction.
Step 1 | List items by room and stable reference.
Step 2 | Reconcile quantities with the furnished plan.
Step 3 | Confirm specification, approval, purchasing responsibility, and delivery constraints before ordering.
Room | Use a stable room name or number.
Reference | Match the plan and product specification.
Item | Describe the proposed selection.
Quantity | Count items; do not confuse a set with individual units.
Unit | Use an explicit purchasing unit.
Specification reference | Point to the current product specification.
Approval | Track selection approval separately from an order.
Order / delivery | Record actual order status only when confirmed.
Review note | Identify missing model, access, or suitability information.

## Blank Template
FF&E schedule template
Blank editable template • Complete with your own verified project information.
Units: explicitly stated per entry • Nominal example dimensions require site verification.
Read Instructions first. Keep source, status, and unresolved information visible.
Room | Reference | Item | Quantity | Unit | Specification reference | Approval | Order / delivery | Review note

## Worked Example
FF&E schedule template
Illustrative teaching extension of The Window Room; not a client record, supplier quote, site survey, or construction-ready document. Pending professional review.
Units: explicitly stated per entry • Nominal example dimensions require site verification.
Read Instructions first. Keep source, status, and unresolved information visible.
Room | Reference | Item | Quantity | Unit | Specification reference | Approval | Order / delivery | Review note
The Window Room | F-01 | Linen two-seat sofa | 1 | item | F-01; product details to develop | Pending review | Not ordered | Illustrative selection; final model to be specified
The Window Room | F-02 | Oak reading chair | 1 | item | F-02; product details to develop | Pending review | Not ordered | Oak frame with linen upholstery
The Window Room | T-01 | Undyed wool rug | 1 | item | T-01; product details to develop | Pending review | Not ordered | 2400 × 1800 mm illustrative size