## Instructions
Interior design project timeline template | OpenLintel • Editable XLSX resource
How to use | The worked example shows sequence, not a promised duration. Enter dates only after confirming scope, decision availability, and supplier information. Keep dependencies understandable rather than hiding them in an unsupported automatic scheduler. When a prerequisite changes, review affected dates with their owners and preserve the reason for the revision.
Example status | Illustrative teaching extension of The Window Room; not a client record, supplier quote, site survey, or construction-ready document. Pending professional review.
Getting started | Duplicate Blank Template for your project. Replace teaching examples with verified project information. Keep units and sources explicit. Nothing is uploaded to OpenLintel.
Units / currency | State units explicitly. Sample dimensions are metric and nominal, not surveyed.
Review | These are educational planning aids, not legal agreements, professional certification, or instructions for construction.
Step 1 | List phase outputs before adding dates.
Step 2 | Name dependencies and the people responsible for reviews.
Step 3 | Revise future dates when a prerequisite changes and record the reason.
Phase | Name a phase or work package.
Output | State what must exist at the end.
Owner | Assign a real person or role when agreed.
Planned start | Enter a project-specific date; example intentionally blank.
Planned finish | Allow time for review rather than assuming instant approval.
Depends on | Name the prerequisite output or decision.
Review milestone | Describe the decision that allows progress.
Status | Record an actual state, not a guessed completion percentage.

## Blank Template
Interior design project timeline template
Blank editable template • Complete with your own verified project information.
Units: explicitly stated per entry • Nominal example dimensions require site verification.
Read Instructions first. Keep source, status, and unresolved information visible.
Phase | Output | Owner | Planned start | Planned finish | Depends on | Review milestone | Status

## Worked Example
Interior design project timeline template
Illustrative teaching extension of The Window Room; not a client record, supplier quote, site survey, or construction-ready document. Pending professional review.
Units: explicitly stated per entry • Nominal example dimensions require site verification.
Read Instructions first. Keep source, status, and unresolved information visible.
Phase | Output | Owner | Planned start | Planned finish | Depends on | Review milestone | Status
Discovery | Agreed brief and information requests | To appoint |  |  | Project information | Confirm objectives and constraints | Planning example
Concept | Selected material direction | To appoint |  |  | Brief review | Select Quiet Oak or revise direction | Planning example
Coordination | WR-01, WR-02, partial material schedule | To appoint |  |  | Concept selection and verified inputs | Review references and open issues | Planning example
Handoff | Indexed issue package | To appoint |  |  | Coordination review | Confirm recipients and outstanding actions | Planning example